## Sheet1
Man Power Event Planner
Activity: |  |  |  | Date of Activity:
Event Contact:
School Contact:
|  |  | Responsible | Comments
One Month Before Event
School Master Calendar
Schedule Room(s) For Activity
Notify Office Staff/Custodian/Etc.
Schedule Childcare Room
Reserve Equipment/Technology
Schedule/Confirm Presenter
Two Weeks Before Event
Submit to newsletter
Inform staff
Flyer, Invitation, Reminders
Promotional materials to translation
Print arrangements
Marketing Dept. Tip Sheet (2 weeks prior)
Schedule Interpreter
Schedule childcare
Distribute flyer at all school events
Organize volunteers for event
One Week Before Event
Order Food (at least 7 days prior to event if using SSC)
ParentLink call
Phone calls (personal)
Remind volunteers of assigned tasks
One Day Before Event
Confirm food/snack order
Notify kitchen staff about delivery
Confirm childcare
Day of Event by 2:00 PM
Agenda
Handouts (compile or acquire from Presenter)
Evaluation/Reflection
Plan room layout
Sign In Sheets/clipboards/pencils
Signage (Welcome, Directional, etc.)
Day of Event by 30 min prior
Set up food area/drinks
Set out handouts
Set out sign-in sheets
Handouts (compile or acquire from Presenter)
Set out supplies needed
Follow Up
Recap E-mail to Staff
Compile/Report Feedback
Thank You Notes/Letters
Submit Recap to Newsletter
EVENT ASSIGNMENTS
Our goal is to be inclusive. Have all appropriate staff members, community members and fathers been invited to participate?
Room Set Up/Decorate | Sign In | Greeter/Host | Refreshments | Technology/Childcare | Clean-UP
Presenter(s):
Comments (special considerations, volunteer help needed, etc.):